## Sheet1
Novel plan - 2014
| Writing | Publishing | Marketing
January | From Jan 8th Draft three of Lycopolis #2. |  | Update Amazon page for Lycopolis, and my author page.
February | Draft three of Lycopolis #2. |  | Post on Lycopolis blog. Tweets, Facebook.
March | Draft three of Lycopolis #2. |  | New Lycopolis short story. Tweets, Facebook.
April | To April 17th Draft three of Lycopolis #2. | Lycopolis #2 to editor by April 17th. | StoryCartel for Lycopolis.
May | writing break / short stories |  | Focus on marketing Lycopolis this month.
June | Edit Lycopolis #2 based on feedback. |  | Create marketing plan for second part of the year.
July | Edit Lycopolis #2 based on feedback. | Publish Lycopolis #2 by July 31st. | Send review copies of Lycopolis #2 out. Update website with details of Lycopolis #2.
August | Draft one of Lycopolis #3. (Already have 20,000 words.) |  | Review marketing results so far; create marketing plan for the rest of the year.
September | Draft one of Lycopolis #3 finished by Sept 30th.
October | Draft two of Lycopolis #3. |  | Hallowe'en - promote Lycopolis.
November | Draft two of Lycopolis #3.
December | Draft two complete by December 25th. | Plan to send Lycopolis #3 to editor in January.
Words per day | 900
Per month... | 27000
Three months.... | 81000 | equals one novel draft
Per year... | 328500 |  | www.aliventures.com